{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":55,"n_cols":10,"rows_kept":55}
[]
[null,"Data Date","2026-02-04"]
[null,"Project Name","AZTAC Lmited"]
[null,"Layout Name","30d lookahead"]
[null,"Weekend","Saturday, Sunday"]
[]
[null,"Level 1","Task ID","Task Name","Task Type","Start","Finish","% Completed","Predecessor","Predecessor Details"]
[null,"Substructure","A101","Start","Start Milestone","2026-02-01",null,{"v":1,"d":"100%"}]
[null,"Substructure","A102","Excavation","Task Dependent",{"$f":"F8+1","v":"2026-02-02"},{"$f":"F9+1","v":"2026-02-03"},{"v":1,"d":"100%"},"A101","A101: FS"]
[null,"Substructure","A103","PCC","Task Dependent",{"$f":"F9+1","v":"2026-02-03"},{"$f":"F10+4","v":"2026-02-07"},{"v":0.25,"d":"25%"},"A102","A102: FS"]
[null,"Substructure","A104","Curing","Task Dependent","2026-02-04",{"$f":"F11+6","v":"2026-02-10"},{"v":0.02,"d":"2%"},"A103","A103: FS"]
[null,"Superstructure","A105","Side Shutter","Task Dependent","2026-02-05",{"$f":"F12+4","v":"2026-02-09"},{"v":0,"d":"0%"},"A104","A104: FS"]
[null,"Superstructure","A106","Rebar","Task Dependent",{"$f":"F12+1","v":"2026-02-06"},{"$f":"F13+6","v":"2026-02-12"},{"v":0,"d":"0%"},"A105","A105: FS"]
[null,"Superstructure","A107","Concrete","Task Dependent",{"$f":"G13+1","v":"2026-02-13"},{"$f":"F14+2","v":"2026-02-15"},{"v":0,"d":"0%"},"A106","A106: FS"]
[null,"Superstructure","A108","Task 1","Task Dependent",{"$f":"G14+1","v":"2026-02-16"},{"$f":"F15+6","v":"2026-02-22"},{"v":0,"d":"0%"},"A107","A107: FS"]
[null,"Finishes","A109","Task 2","Task Dependent",{"$f":"G15+1","v":"2026-02-23"},{"$f":"F16+6","v":"2026-03-01"},{"v":0,"d":"0%"},"A108","A108: FS"]
[null,"Finishes","A110","Task 3","Task Dependent","2026-03-02","2026-03-08",{"v":0,"d":"0%"},"A109","A109: FS"]
[null,"Finishes","A111","Task 4","Task Dependent","2026-03-09","2026-03-15",{"v":0,"d":"0%"},"A110","A110: FS"]
[null,"Finishes","A112","Task 5","Task Dependent","2026-03-16","2026-03-22",{"v":0,"d":"0%"},"A111","A111: FS"]
[null,"Finishes","A113","Task 6","Task Dependent","2026-03-23","2026-03-29",{"v":0,"d":"0%"},"A112","A112: FS"]
[null,"Finishes","A114","Task 7","Task Dependent","2026-03-30","2026-04-05",{"v":0,"d":"0%"},"A113","A113: FS"]
[null,"Finishes","A115","Task 8","Task Dependent","2026-04-06","2026-04-12",{"v":0,"d":"0%"},"A114","A114: FS"]
[null,"Finishes","A1145","Task 90","Finish Milestone",null,"2028-01-22",{"v":0,"d":"0%"},"A115","A114: FF"]
[null,"Finishes","A2900","Task 80","Finish Milestone",null,"2028-01-12",{"v":0,"d":"0%"}]
[null,"Finishes","A116","Task 9","Task Dependent",{"$f":"G22+1","v":"2026-04-13"},"2026-04-19",{"v":0,"d":"0%"},"A115","A115: FS"]
[null,"Section 04","A117","Task 10","Task Dependent",{"$f":"G25+1","v":"2026-04-20"},{"$f":"F26+30","v":"2026-05-20"},{"v":0,"d":"0%"},"A116","A116: FS"]
[null,"Section 04","A118","Task 11","Task Dependent",{"$f":"G26+1","v":"2026-05-21"},{"$f":"F27+30","v":"2026-06-20"},{"v":0,"d":"0%"},"A117","A117: FS"]
[null,"Section 04","A119","Task 12","Task Dependent","2026-06-21","2026-07-21",{"v":0,"d":"0%"},"A118","A118: FS"]
[null,"Section 04","A120","Task 13","Task Dependent","2026-07-22","2026-08-21",{"v":0,"d":"0%"},"A119","A119: FS"]
[null,"Section 04","A121","Task 14","Task Dependent","2026-08-22","2026-09-21",{"v":0,"d":"0%"},"A120","A120: FS"]
[null,"Section 04","A122","Task 15","Task Dependent","2026-09-22","2026-10-22",{"v":0,"d":"0%"},"A121","A121: FS"]
[null,"Section 04","A123","Task 16","Task Dependent","2026-10-23","2026-11-22",{"v":0,"d":"0%"},"A122","A122: FS"]
[null,"Section 04","A124","Task 17","Task Dependent","2026-11-23","2026-12-23",{"v":0,"d":"0%"},"A123","A123: FS"]
[null,"Section 04","A125","Task 18","Task Dependent","2026-12-24","2027-01-23",{"v":0,"d":"0%"},"A124","A124: FS"]
[null,"Section 04","A126","Task 19","Task Dependent","2027-01-24","2027-02-23",{"v":0,"d":"0%"},"A125","A125: FS"]
[null,"Section 05","A127","Task 20","Task Dependent","2027-02-24","2027-03-26",{"v":0,"d":"0%"},"A126","A126: FS"]
[null,"Section 05","A128","Task 21","Task Dependent","2027-03-27","2027-04-26",{"v":0,"d":"0%"},"A127","A127: FS"]
[null,"Section 05","A129","Task 22","Task Dependent","2027-04-27","2027-05-27",{"v":0,"d":"0%"},"A128","A128: FS"]
[null,"Section 05","A130","Task 23","Task Dependent","2027-05-28","2027-06-27",{"v":0,"d":"0%"},"A129","A129: FS"]
[null,"Section 05","A131","Task 24","Task Dependent","2027-06-28","2027-07-28",{"v":0,"d":"0%"},"A130","A130: FS"]
[null,"Section 05","A132","Task 25","Task Dependent","2027-07-29","2027-08-28",{"v":0,"d":"0%"},"A131","A131: FS"]
[null,"Section 05","A133","Task 26","Task Dependent","2027-08-29","2027-09-28",{"v":0,"d":"0%"},"A132","A132: FS"]
[null,"Section 05","A134","Task 27","Task Dependent",{"$f":"F42","v":"2027-08-29"},"2027-09-28",{"v":0,"d":"0%"},"A133","A133: SS"]
[null,"Section 05","A135","Task 28","Task Dependent","2027-09-29","2027-10-29",{"v":0,"d":"0%"},"A134, A1145, A1145","A134: FS, A1145: FS, A1145: FF"]
[null,"Section 05","A136","Task 29","Task Dependent","2027-10-30","2027-11-29",{"v":0,"d":"0%"},"A135","A135: FS"]
[null,"Section 05","A137","Task 30","Task Dependent","2027-11-30","2027-12-30",{"v":0,"d":"0%"},"A136","A136: FS"]
[null,"Section 05","A138","Task 31","Task Dependent","2027-12-31","2028-01-30",{"v":0,"d":"0%"},"A137","A137: FS"]
[null,"Section 06","A139","Task 32","Task Dependent","2028-01-31","2028-03-01",{"v":0,"d":"0%"},"A138, A2900","A138: FS, A2900: FS"]
[null,"Section 06","A140","Task 33","Task Dependent","2028-03-02","2028-04-01",{"v":0,"d":"0%"},"A139","A139: FS"]
[null,"Section 06","A141","Task 34","Task Dependent","2028-04-02","2028-05-02",{"v":0,"d":"0%"},"A140","A140: FS"]
[null,"Section 06","A142","Task 35","Task Dependent","2028-05-03","2028-06-02",{"v":0,"d":"0%"},"A141","A141: FS"]
[null,"Section 06","A143","Task 36","Task Dependent","2028-06-03","2028-07-03",{"v":0,"d":"0%"},"A142","A142: FS"]
[null,"Section 06","A144","Task 37","Task Dependent","2028-07-04","2028-08-03",{"v":0,"d":"0%"},"A143","A143: FS"]
[null,"Section 06","A145","Task 38","Task Dependent","2028-08-04","2028-09-03",{"v":0,"d":"0%"},"A144","A144: FS"]
[null,"Section 06","A146","Finish","Finish Milestone",null,{"$f":"G54","v":"2028-09-03"},{"v":0,"d":"0%"},"A145","A145:FF"]