{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":22,"n_cols":10,"rows_kept":22}
[]
[null,"Data Date","2026-05-25"]
[null,"Project Name","Carbody"]
[null,"Layout Name","High Level View"]
[null,"Weekend","Saturday, Sunday"]
[]
[null,"Level 1","Task ID","Task Name","Task Type","Start","Finish","% Completed","Predecessor","Predecessor Details"]
[null,"Phase 0","A102","Engineering Package 01 Confirm","Finish Milestone",null,"2025-09-23",{"v":1,"d":"100%"}]
[null,"Phase 0","A103","Engineering Package 02 Confirm","Finish Milestone",null,"2025-10-09",{"v":1,"d":"100%"}]
[null,"Phase 0","A104","Engineering Package 03 Confirm","Finish Milestone",null,"2025-12-02",{"v":1,"d":"100%"}]
[null,"Phase 0","A110","Engineering Package 04 Confirm","Finish Milestone",null,"2026-06-09",{"v":0,"d":"0%"}]
[null,"Phase 0","A105","Engineering Package 05 Confirm","Finish Milestone",null,"2025-08-16",{"v":1,"d":"100%"}]
[null,"Phase 0","A106","Engineering Package 06 Confirm","Finish Milestone",null,"2025-12-17",{"v":1,"d":"100%"}]
[null,"Phase 01","A107","Production - Carbody","Task Dependent","2026-03-26","2026-06-29",{"v":0.65,"d":"65%"},"A102, A105","A102: FS, A105: FS"]
[null,"Phase 01","A108","Production - Fitouts","Task Dependent","2026-03-26","2026-06-29",{"v":0.65,"d":"65%"},"A103, A105","A103: FS, A105: FS"]
[null,"Phase 02","A109","Testing - Carbody","Task Dependent","2026-03-26","2026-06-29",{"v":0.65,"d":"65%"},"A104, A106","A104: FS, A106: FS"]
[null,"Phase 03","A111","Testing - Complete Car","Task Dependent",{"$f":"G16+1","v":"2026-06-30"},"2026-07-31",{"v":0,"d":"0%"},"A107, A108, A109, A110","A107: FS, A108: FS, A109: FS, A110:FS"]
[null,"Phase 04","A112","Test Reports and Validation","Task Dependent",{"$f":"G17+1","v":"2026-08-01"},"2026-08-31",{"v":0,"d":"0%"},"A111","A111: FS"]
[null,"Final","A116","As-Build Drawings","Task Dependent",{"$f":"G18+1","v":"2026-09-01"},"2026-09-29",{"v":0,"d":"0%"},"A112","A112: FS"]
[null,"Final","A113","Handover of Carbody","Finish Milestone",null,{"$f":"G19+1","v":"2026-09-30"},{"v":0,"d":"0%"},"A116","A116: FS"]
[null,"Final","A114","Final Carbody Report","Task Dependent",{"$f":"G20+1","v":"2026-10-01"},{"$f":"F21+24","v":"2026-10-25"},{"v":0,"d":"0%"},"A113","A113: FS"]
[null,"Final","A115","Completion","Finish Milestone",null,{"$f":"G21","v":"2026-10-25"},{"v":0,"d":"0%"},"A114","A114: FF"]